## Dashboard
LEGAL RISK DASHBOARD — holilabsv2
Healthcare / HealthTech — LGPD, HIPAA, ANVISA, COFEPRIS
Assessment Date: 2026-03-18 ¦ Next Review: 2026-04-18
Total Risks | Critical | High | Medium | Low | Open
12 | 2 | 7 | 3 | 0 | 11
RISKS BY CATEGORY
Category | Count | Avg Score | Max Score | Critical/High Count
Data Privacy | 3 | 14.6667 | 0 | 2
Regulatory | 3 | 12.6667 | 0 | 2
Security | 2 | 9 | 0 | 1
Data Breach | 1 | 15 | 0 | 1
Consent | 1 | 12 | 0 | 1
AI Ethics | 1 | 12 | 0 | 1
Contract | 1 | 12 | 0 | 1
REGULATORY COMPLIANCE STATUS
Status | Count
Strong | 1
In Progress | 1
Partial | 3
Gap | 4
Not Started | 1
TOP PRIORITY ACTIONS
1. Execute SCCs for all LLM provider cross-border data transfers (LGPD Art. 33) — Owner: RUTH — Due: 2026-06-30
2. Complete BAAs with remaining 5 AI subprocessors (HIPAA) — Owner: CYRUS — Due: 2026-05-31
3. Prepare ANVISA SaMD classification dossier for CDSS module — Owner: RUTH — Due: 2026-09-30
4. Refactor consent UI to enforce 4-tier granular consent model — Owner: RUTH + PAUL — Due: 2026-05-15
5. Conduct demographic bias audit on AI confidence scoring — Owner: ELENA — Due: 2026-06-30
6. Schedule first incident response tabletop exercise — Owner: CYRUS — Due: 2026-04-30
7. Map full data lineage for erasure request propagation — Owner: CYRUS + RUTH — Due: 2026-06-30

## Risk Register
Risk ID | Date Identified | Last Updated | Category | Sub-Category | Risk Description | Affected Regulation(s) | Jurisdiction(s) | Severity (1-5) | Likelihood (1-5) | Risk Score | Risk Level | Risk Velocity | Detectability (1-5) | RPN | Control Effectiveness | Residual Severity | Residual Likelihood | Residual Score | Residual Level | Risk Owner | Mitigation Strategy | Current Controls | Status | Review Cadence | Next Review Date | Escalation Required? | Outside Counsel? | Board Reporting? | Notes / Linked Documents
DP-001 | 2026-03-18 | 2026-03-18 | Data Privacy | LGPD Compliance | Cross-border transfer of patient PHI to US-hosted LLM providers without ANPD-approved transfer mechanism (LGPD Art. 33) | LGPD Art. 33, ANPD Res. 19/2024 | Brazil | 5 | 4 | 20 | CRITICAL | Fast | 3 | 60 | Partial | 4 | 3 | 12 | HIGH | DPO / RUTH | Implement SCCs + DPIA; evaluate local inference | Data anonymization layer before LLM calls; contractual DPA with providers | Open | Monthly | 2026-04-18 | Yes | Yes | No | Link to DPIA-2026-003
DP-002 | 2026-03-18 | 2026-03-18 | Data Privacy | HIPAA PHI Exposure | Patient PII/PHI fields (CPF, CNS, clinical notes) transmitted to third-party AI without BAA in place | HIPAA Privacy Rule, HIPAA Security Rule | United States | 5 | 3 | 15 | HIGH | Fast | 2 | 30 | Weak | 4 | 2 | 8 | MEDIUM | CISO / CYRUS | Execute BAAs with all AI subprocessors; implement field-level encryption | encryptPHIWithVersion on CPF/CNS fields; audit log hash-chain | Open | Monthly | 2026-04-18 | Yes | Yes | Yes | BAA tracker in docs/legal/
REG-001 | 2026-03-18 | 2026-03-18 | Regulatory | SaMD Classification | CDSS triage module may constitute SaMD Class II under ANVISA RDC 657/2022 if it influences clinical decisions beyond information display | ANVISA RDC 657/2022, IEC 62304, ISO 13485 | Brazil, LATAM | 5 | 4 | 20 | CRITICAL | Moderate | 3 | 60 | Partial | 4 | 3 | 12 | HIGH | CLO / RUTH | Engage ANVISA regulatory counsel; prepare classification dossier | UI disclaimers; clinical provenance metadata on all rules; human-in-the-loop gate | Open | Bi-weekly | 2026-04-01 | Yes | Yes | Yes | CDSS_IMPLEMENTATION_GUIDE.md
REG-002 | 2026-03-18 | 2026-03-18 | Regulatory | Telemedicine AI Limits | AI-assisted clinical recommendations may exceed CFM Resolução 2.314/2022 boundaries for AI in telemedicine | CFM Res. 2.314/2022 | Brazil | 4 | 3 | 12 | HIGH | Moderate | 3 | 36 | Partial | 3 | 2 | 6 | MEDIUM | CMO / ELENA | Ensure human review gate on all AI outputs; document compliance mapping | Manchester triage requires physician sign-off; AI confidence scoring with thresholds | Open | Monthly | 2026-04-18 | Yes | Consider | No | AI_CONFIDENCE_SCORING_IMPLEMENTATION.md
SEC-001 | 2026-03-18 | 2026-03-18 | Security | Tenant Isolation Breach | Cross-tenant data leakage risk in multi-tenant architecture if row-level security or verifyPatientAccess() is bypassed | LGPD Art. 46, HIPAA Security Rule | Brazil, US | 5 | 2 | 10 | HIGH | Fast | 2 | 20 | Strong | 4 | 1 | 4 | LOW | CISO / CYRUS | Penetration testing; row-level security audit; circuit breaker monitoring | createProtectedRoute RBAC guard; verifyPatientAccess() on all patient endpoints; tenant-scoped queries | Open | Quarterly | 2026-06-18 | No | No | No
SEC-002 | 2026-03-18 | 2026-03-18 | Security | Audit Trail Integrity | Risk of audit log tampering or deletion violating LGPD Art. 37 retention requirements and hash-chain integrity | LGPD Art. 37, SOC 2 CC7.2 | Brazil, US | 4 | 2 | 8 | MEDIUM | Slow | 2 | 16 | Strong | 3 | 1 | 3 | LOW | CISO / CYRUS | Append-only storage; cryptographic hash-chain verification; immutable backups | Hash-chain AuditLog; GovernanceEvent immutability; scheduled integrity checks | Mitigated | Quarterly | 2026-06-18 | No | No | No
BREACH-001 | 2026-03-18 | 2026-03-18 | Data Breach | Breach Notification | Failure to meet 72-hour ANPD notification deadline or 60-day HHS notification for breaches affecting >500 individuals | LGPD Art. 48, HIPAA Breach Notification Rule | Brazil, US | 5 | 3 | 15 | HIGH | Fast | 3 | 45 | Partial | 4 | 2 | 8 | MEDIUM | DPO / RUTH + CYRUS | Incident response playbook; pre-drafted notification templates; tabletop exercises | Incident response runbook; pre-approved BAA email templates; monitoring alerts | Open | Quarterly | 2026-06-18 | Yes | Yes | Yes | BAA_EMAIL_TEMPLATES_READY_TO_SEND.md
CONSENT-001 | 2026-03-18 | 2026-03-18 | Consent | Granular Consent | Single-checkbox consent flow that collapses treatment, research, and AI processing consent into one action, violating LGPD granularity requirements | LGPD Art. 8, Art. 11 | Brazil | 4 | 3 | 12 | HIGH | Moderate | 3 | 36 | Partial | 3 | 2 | 6 | MEDIUM | CLO / RUTH | Implement 4-tier consent: treatment, research, AI processing, data sharing | Consent management module in shared-kernel; withdrawal API endpoint | Open | Monthly | 2026-04-18 | No | Consider | No
AI-001 | 2026-03-18 | 2026-03-18 | AI Ethics | Algorithmic Bias | Clinical decision support algorithms may exhibit demographic bias (age, ethnicity, socioeconomic) in triage or biomarker interpretation | LGPD Art. 20, EU AI Act (reference), CFM Res. 2.314 | Brazil, LATAM | 4 | 3 | 12 | HIGH | Slow | 4 | 48 | Weak | 3 | 2 | 6 | MEDIUM | CMO / ELENA | Bias auditing framework; demographic parity monitoring; explainability requirements | AI confidence scoring; Tier 1-3 evidence source classification; human review gate | Open | Quarterly | 2026-06-18 | No | Consider | No
CONTRACT-001 | 2026-03-18 | 2026-03-18 | Contract | Vendor DPA Gaps | Third-party AI/cloud vendors processing PHI without adequate DPAs or sub-processor controls per LGPD/HIPAA | LGPD Art. 39-40, HIPAA BAA Requirements | Brazil, US | 4 | 3 | 12 | HIGH | Moderate | 3 | 36 | Partial | 3 | 2 | 6 | MEDIUM | CLO / RUTH | DPA/BAA audit of all vendors; standardized DPA template; sub-processor registry | Existing BAAs with primary cloud providers; DPA review checklist | Open | Quarterly | 2026-06-18 | No | Consider | No
ERASURE-001 | 2026-03-18 | 2026-03-18 | Data Privacy | Right to Erasure | Data subject erasure requests may fail to propagate to all systems (backups, LLM training data, analytics) within LGPD-mandated timelines | LGPD Art. 18(VI), HIPAA Right of Access | Brazil, US | 3 | 3 | 9 | MEDIUM | Moderate | 3 | 27 | Partial | 2 | 2 | 4 | LOW | DPO / RUTH + CYRUS | Cryptographic erasure pipeline; data lineage mapping; automated propagation | Erasure API endpoint with legalBasis field; AuditLog retention exception per LGPD Art. 37 | Open | Monthly | 2026-04-18 | No | No | No
COFEPRIS-001 | 2026-03-18 | 2026-03-18 | Regulatory | Mexico SaMD | Expansion into Mexico market requires COFEPRIS classification and registration for clinical decision support modules | COFEPRIS Medical Device Regulations | Mexico | 3 | 2 | 6 | MEDIUM | Slow | 4 | 24 | None | 3 | 2 | 6 | MEDIUM | CLO / RUTH | Engage Mexican regulatory counsel; prepare COFEPRIS pre-submission; timeline assessment | No controls in place — pre-market entry phase | Open | Quarterly | 2026-06-18 | No | Yes | No

## Heat Map
RISK HEAT MAP — Severity × Likelihood
Severity ↓ / Likelihood → | Remote (1) | Unlikely (2) | Possible (3) | Likely (4) | Almost Certain (5)
Critical (5) | 5 | 10 | 15 | 20 | 25
High (4) | 4 | 8 | 12 | 16 | 20
Moderate (3) | 3 | 6 | 9 | 12 | 15
Low (2) | 2 | 4 | 6 | 8 | 10
Negligible (1) | 1 | 2 | 3 | 4 | 5
RISK PLACEMENT
Risk ID | Severity | Likelihood | Score | Level | Quadrant Action
DP-001 | 5 | 4 | 20 | CRITICAL | IMMEDIATE ACTION
DP-002 | 5 | 3 | 15 | HIGH | MITIGATION PLAN
REG-001 | 5 | 4 | 20 | CRITICAL | IMMEDIATE ACTION
REG-002 | 4 | 3 | 12 | HIGH | MITIGATION PLAN
SEC-001 | 5 | 2 | 10 | HIGH | MITIGATION PLAN
SEC-002 | 4 | 2 | 8 | MEDIUM | MONITOR & REVIEW
BREACH-001 | 5 | 3 | 15 | HIGH | MITIGATION PLAN
CONSENT-001 | 4 | 3 | 12 | HIGH | MITIGATION PLAN
AI-001 | 4 | 3 | 12 | HIGH | MITIGATION PLAN
CONTRACT-001 | 4 | 3 | 12 | HIGH | MITIGATION PLAN
ERASURE-001 | 3 | 3 | 9 | MEDIUM | MONITOR & REVIEW
COFEPRIS-001 | 3 | 2 | 6 | MEDIUM | MONITOR & REVIEW

## Regulatory Mapping
Regulation | Jurisdiction | Applicable To | Key Requirements | Penalty / Fine Range | Enforcement Trend | Compliance Status | Gap Description | Remediation Owner | Target Date | Priority
LGPD (Lei 13.709/2018) | Brazil | All patient data processing | Lawful basis, consent granularity, DPO appointment, DPIA, cross-border transfer controls, breach notification (72h) | Up to R$50M per infraction or 2% of revenue | Increasing — ANPD issuing sectoral guidance for health | Partial | Cross-border LLM transfers lack approved mechanism; consent granularity incomplete | DPO / RUTH | 2026-06-30 | P0
HIPAA Privacy Rule | United States | PHI of US patients or US-based operations | Minimum necessary standard, patient access rights, accounting of disclosures, BAA requirements | Up to $2.1M per violation category per year; criminal penalties possible | Active — HHS OCR investigating AI-related PHI exposures | Partial | BAAs needed with AI subprocessors; accounting of disclosures for AI processing | CISO / CYRUS | 2026-05-31 | P0
HIPAA Security Rule | United States | ePHI systems and infrastructure | Administrative, physical, technical safeguards; risk analysis; encryption; access controls; audit controls | Same as Privacy Rule | Active enforcement | Strong | Annual risk analysis due; encryption audit for new AI pipeline | CISO / CYRUS | 2026-06-30 | P1
ANVISA RDC 657/2022 | Brazil | CDSS / clinical triage module | SaMD classification (I-IV), QMS (ISO 13485), software lifecycle (IEC 62304), clinical evidence | Product recall, market withdrawal, fines | New regulation — enforcement building | Gap | No classification dossier prepared; QMS not formalized for CDSS module | CLO / RUTH | 2026-09-30 | P0
CFM Res. 2.314/2022 | Brazil | AI-assisted clinical recommendations | Physician oversight of AI in telemedicine; transparency of AI involvement; patient consent for AI | Professional sanctions; practice restrictions | Moderate enforcement | Partial | Need explicit patient notification of AI involvement in triage | CMO / ELENA | 2026-06-30 | P1
IEC 62304 | International | Medical device software lifecycle | Software safety classification, development process, maintenance, risk management | Prerequisite for SaMD registration | Standard requirement | Gap | No formal software lifecycle documentation per IEC 62304 for CDSS | CTO / ARCHIE | 2026-09-30 | P1
ISO 13485 | International | Quality management system for medical devices | QMS establishment, document control, design controls, CAPA, management review | Prerequisite for SaMD registration | Standard requirement | Gap | No QMS in place for CDSS module | CLO / RUTH | 2026-09-30 | P1
COFEPRIS | Mexico | Clinical software for Mexico market | Medical device registration, classification, post-market surveillance | Market entry prohibition; fines | Moderate — expanding digital health regulation | Not Started | Pre-market entry — full regulatory pathway required | CLO / RUTH | 2026-12-31 | P2
SOC 2 Type II | United States | Infrastructure and data handling | Trust service criteria: security, availability, processing integrity, confidentiality, privacy | Customer trust / contract requirement | Market expectation for B2B healthtech | In Progress | Controls documented; audit scheduled | CISO / CYRUS | 2026-09-30 | P1
ANPD Res. 19/2024 | Brazil | International data transfers | Standard contractual clauses, adequacy assessments, binding corporate rules | Covered under LGPD penalties | New — first enforcement actions expected 2026 | Gap | No SCCs executed for LLM provider data transfers | DPO / RUTH | 2026-06-30 | P0

## Controls Assessment
Control ID | Control Name | Control Type | Control Category | Description | Linked Risk ID(s) | Linked Regulation(s) | Implementation Status | Design Effectiveness | Operating Effectiveness | Test Method | Last Tested | Test Result | Gap / Finding | Remediation Plan | Owner | Target Date
CTRL-001 | Field-Level PHI Encryption | Technical | Data Protection | encryptPHIWithVersion applied to CPF, CNS, RG, clinical notes before database write | DP-001, DP-002, SEC-001 | LGPD Art. 46, HIPAA Security Rule | Implemented | Effective | Effective | Code review + penetration test | 2026-02-15 | Pass |  |  | CYRUS
CTRL-002 | RBAC Route Protection | Technical | Access Control | createProtectedRoute guard on all patient-facing API endpoints with role verification | SEC-001 | HIPAA Security Rule, LGPD Art. 46 | Implemented | Effective | Effective | Automated test suite + manual audit | 2026-03-01 | Pass |  |  | CYRUS
CTRL-003 | Audit Log Hash-Chain | Technical | Audit Trail | Append-only AuditLog with cryptographic hash-chain; GovernanceEvent immutability enforced | SEC-002 | LGPD Art. 37, SOC 2 CC7.2 | Implemented | Effective | Effective | Integrity verification script | 2026-03-10 | Pass |  |  | CYRUS
CTRL-004 | Granular Consent Management | Administrative | Consent | 4-tier consent flow: treatment, research, AI processing, data sharing with individual withdrawal | CONSENT-001 | LGPD Art. 8, Art. 11 | Partial | Needs Improvement | Not Tested | UI review + consent audit |  | N/A | Single checkbox still in some flows | Refactor consent UI to enforce 4-tier model | RUTH + PAUL | 2026-05-15
CTRL-005 | AI Confidence Scoring | Technical | Clinical Safety | AI outputs tagged with confidence score; threshold gates require human review below threshold | REG-002, AI-001 | CFM Res. 2.314/2022 | Implemented | Effective | Partially Effective | Clinical validation study | 2026-02-28 | Conditional Pass | Threshold calibration needed for edge demographics | Bias audit across demographic groups | ELENA | 2026-06-30
CTRL-006 | LLM Data Anonymization Layer | Technical | Data Protection | PII/PHI stripped or anonymized before transmission to external LLM providers | DP-001, DP-002 | LGPD Art. 33, HIPAA Privacy Rule | Implemented | Partially Effective | Partially Effective | Data leakage testing | 2026-03-05 | Conditional Pass | Some clinical context may allow re-identification | Implement k-anonymity validation; differential privacy analysis | CYRUS | 2026-06-30
CTRL-007 | Vendor BAA/DPA Registry | Administrative | Third-Party Risk | Central registry tracking BAA/DPA status with all vendors processing PHI/PII | CONTRACT-001, DP-002 | HIPAA BAA, LGPD Art. 39-40 | Partial | Needs Improvement | Not Tested | Registry completeness audit |  | N/A | 3 of 8 AI vendors lack executed BAAs | Execute remaining BAAs; add to vendor onboarding checklist | RUTH | 2026-05-31
CTRL-008 | Incident Response Playbook | Administrative | Breach Response | Documented incident response with roles, notification timelines, and pre-drafted templates | BREACH-001 | LGPD Art. 48, HIPAA Breach Notification | Implemented | Effective | Not Tested | Tabletop exercise |  | N/A | No tabletop exercise conducted yet | Schedule quarterly tabletop exercise | CYRUS + RUTH | 2026-04-30
CTRL-009 | Clinical Rule Provenance | Technical | Clinical Safety | All clinical rules tagged with sourceAuthority, citationUrl, evidenceTier metadata | REG-001, AI-001 | ANVISA RDC 657/2022, IEC 62304 | Implemented | Effective | Effective | Automated metadata validation | 2026-03-12 | Pass |  |  | ELENA
CTRL-010 | Data Subject Rights Automation | Technical | Privacy Rights | Automated pipeline for access, portability, and erasure requests with legalBasis field | ERASURE-001 | LGPD Art. 18, HIPAA Right of Access | Partial | Partially Effective | Not Tested | End-to-end request simulation |  | N/A | Erasure propagation to backups and analytics not verified | Map full data lineage; implement cryptographic erasure for backup stores | CYRUS + RUTH | 2026-06-30

## Escalation Matrix
Risk Level | Response Time | Escalation Path | Decision Authority | Outside Counsel? | Board Notification? | Insurance Notification? | Documentation Required | Review Cadence | Example Scenarios
CRITICAL (16-25) | Immediate (same day) | Risk Owner → GC → CEO → Board | CEO / Board | Mandatory | Mandatory | Assess immediately | Full risk memo + crisis plan + board briefing | Daily until resolved | Active PHI breach; ANPD enforcement; government investigation; SaMD recall
HIGH (10-15) | Within 48 hours | Risk Owner → Senior Counsel → GC | General Counsel | Strongly recommended | As needed | Review coverage | Risk memo + mitigation plan + contingency | Weekly | ANVISA classification dispute; threatened litigation; regulatory audit; uncapped vendor liability
MEDIUM (5-9) | Within 1 week | Risk Owner → Legal Team Lead | Legal Team Lead | Consider | No | No | Risk register entry + stakeholder brief | Monthly | DPA gaps with vendors; consent flow deficiency; AI bias detection; regulatory development monitoring
LOW (1-4) | Standard workflow | Risk Owner manages directly | Risk Owner | No | No | No | Risk register entry | Quarterly / Annually | Minor NDA deviation; routine compliance task; standard vendor renewal

## Scoring Guide
RISK SCORING REFERENCE GUIDE
SEVERITY SCALE
Level | Label | Financial Impact | Description
1 | Negligible | < 0.1% of deal/contract value | Minor inconvenience; no material impact; handled within normal operations
2 | Low | < 1% of relevant value | Limited impact; minor financial exposure; minor operational disruption
3 | Moderate | 1-5% of relevant value | Meaningful impact; material exposure; noticeable disruption; limited public attention possible
4 | High | 5-25% of relevant value | Significant impact; substantial exposure; significant disruption; regulatory scrutiny likely
5 | Critical | > 25% of relevant value | Severe impact; major exposure; fundamental disruption; regulatory action likely; personal liability possible
LIKELIHOOD SCALE
Level | Label | Probability | Description
1 | Remote | < 5% | Highly unlikely; no known precedent; would require exceptional circumstances
2 | Unlikely | 5-20% | Could occur but not expected; limited precedent; requires specific triggers
3 | Possible | 20-50% | May occur; some precedent exists; triggering events foreseeable
4 | Likely | 50-80% | Probably will occur; clear precedent; triggering events common
5 | Almost Certain | > 80% | Expected to occur; strong precedent; triggering events present or imminent
RISK VELOCITY SCALE
Velocity | Time to Impact | Description
Slow | > 12 months | Long lead time; allows for planned response and gradual mitigation
Moderate | 3-12 months | Medium lead time; requires proactive planning and resource allocation
Fast | < 3 months | Short lead time; requires immediate attention and rapid response capability
DETECTABILITY SCALE (for RPN)
Level | Label | Description
1 | Almost Certain Detection | Existing controls will almost certainly detect the risk before impact
2 | High Detection | Strong controls; detection is likely with current monitoring
3 | Moderate Detection | Some controls exist; detection is possible but not assured
4 | Low Detection | Weak controls; risk may materialize without advance warning
5 | No Detection | No existing controls; risk will not be detected until impact occurs
CONTROL EFFECTIVENESS RATINGS
Rating | Description
Strong | Control is well-designed and operating effectively; risk is significantly reduced
Partial | Control exists but has gaps in design or operation; provides some risk reduction
Weak | Control exists but is largely ineffective; minimal risk reduction
None | No control in place; risk is fully unmitigated

## Audit Log
Date | Action | Risk/Control ID | Field Changed | Previous Value | New Value | Changed By | Rationale
2026-03-18 | Created | ALL | Initial Assessment | N/A | Initial risk register populated | Legal Risk Assessment Tool | Industry-grade risk assessment for holilabsv2 healthcare platform